## Commctrl APIs and Messages
1994-07-29
J.A.Vinson
Chicago-based Common Controls for NT analysis and progress
This analysis is done based on Chicago code drop dated April 94
Chicago is code dropping late July94 and is not reflected here.
When testing Unicode equivalents in testapps, add "-DUNICODE" to sources file
Make sure code is compiled on ALL supported platforms.
======================================================================
|  | dll | test
OBJECT |  | module | app | progress
======================================================================
Misc:
InitCommonControls() |  | commctrl.c | n/a | done
TOOLBAR APIs and Messages:
CreateMappedBitmap() |  | cutils.c/bmpload.c | tbtnt | done
CreateToolbar() |  | toolbar.c | tbtnt | done
CreateToolbarEx() |  | ?? | tbtnt | needs dll source
TB_ADDBITMAP |  | toolbar.c | tbtnt | done
TB_ADDBITMAP32 |  | toolbar.c | tbtnt | done
TB_ADDBUTTONS |  | toolbar.c | tbtnt | done
TB_ADDSTRINGA |  | toolbar.c | tbtnt | done
TB_ADDSTRINGW |  | ?? | tbtnt | Not Unicoded yet
TB_AUTOSIZE |  | toolbar.c | tbtnt | done
TB_BUTTONCOUNT |  | toolbar.c | tbtnt | done
TB_BUTTONSTRUCTSIZE |  | toolbar.c | tbtnt | done
TB_CHECKBUTTON |  | toolbar.c | tbtnt | done
TB_COMMANDTOINDEX |  | toolbar.c | tbtnt | done
TB_CUSTOMIZE |  | toolbar.c | tbtnt | done
TB_DELETEBUTTON |  | toolbar.c | tbtnt | done
TB_ENABLEBUTTON |  | toolbar.c | tbtnt | done
TB_GETBUTTON |  | toolbar.c | tbtnt | done
TB_GETBUTTONRECT |  | toolbar.c | ?? | needs testapp
TB_GETFONT | conflict?? | commctrl.h | ?? | needs testapp
TB_GETITEMRECT |  | toolbar.c | tbtnt | done
TB_GETSTATE |  | toolbar.c | tbtnt | done
TB_GETTOOLTIPS |  | toolbar.c | ?? | needs testapp
TB_HIDEBUTTON |  | toolbar.c | tbtnt | done
TB_INDETERMINATE |  | toolbar.c | tbtnt | done
TB_INSERTBUTTON |  | toolbar.c | tbtnt | done
TB_ISBUTTONCHECKED |  | toolbar.c | tbtnt | done
TB_ISBUTTONENABLED |  | toolbar.c | tbtnt | done
TB_ISBUTTONHIDDEN |  | toolbar.c | tbtnt | done
TB_ISBUTTONINDETERMINATE |  | toolbar.c | tbtnt | done
TB_ISBUTTONPRESSED |  | toolbar.c | tbtnt | done
TB_PRESSBUTTON |  | toolbar.c | tbtnt | done
TB_SAVERESTOREA |  |  | tbtnt | *UNICODE not done in daytona
TB_SAVERESTOREW |  |  | tbtnt | *UNICODE not done in daytona
TB_SETBITMAPSIZE |  | toolbar.c | tbtnt | needs dll source
TB_SETBUTTON |  | toolbar.c | tbtnt | done
TB_SETBUTTONSIZE |  | toolbar.c | tbtnt | done
TB_SETBUTTONTYPE | Not in Chicago src | ?? | ?? | needs dll and testapp
TB_SETPARENT |  | toolbar.c | ?? | needs testapp
TB_SETSTATE |  | toolbar.c | tbtnt | done
TB_SETTOOLTIPS |  | toolbar.c | ?? | needs testapp
STATUS BAR APIs and Messages:
CreateHeaderWindowA() |  | header.c | tbtnt | done
CreateHeaderWindowW() |  | header.c | tbtnt | done
CreateStatusWindowA() |  | status.c | tbtnt | done
CreateStatusWindowW() |  | status.c | tbtnt | done
DrawStatusTextA() |  | status.c | ?? | needs testapp
DrawStatusTextW() |  | status.c | ?? | needs testapp
HB_ADJUST |  | header.c | tbtnt | done
HB_GETPARTS |  | header.c | tbtnt | done
HB_GETWIDTHS |  | commctrl.h | tbtnt | done
HB_SAVERESTORE |  | header.c | tbtnt | done
HB_SETWIDTHS |  | commctrl.h | tbtnt | done
HB_SHOWTOGGLE |  | header.c | tbtnt | done
SB_GETBORDERS |  | status.c | tbtnt | done
SB_GETPARTS |  | status.c | tbtnt | done
SB_GETTEXTA |  | status.c | tbtnt | done
SB_GETTEXTLENGTH |  | status.c | tbtnt | done
SB_GETTEXTW |  | status.c | tbtnt | done
SB_SETBORDERS |  | status.c | tbtnt | done
SB_SETMINHEIGHT |  | status.c | tbtnt | done
SB_SETPARTS |  | status.c | tbtnt | done
SB_SETTEXTA |  | status.c | tbtnt | done
SB_SETTEXTW |  | status.c | tbtnt | done
SB_SIMPLE |  | status.c | tbtnt | done
MENUHELP APIs and Messages:
GetEffectiveClientRect() |  | menuhelp.c | tbtnt | done
GetPrivateProfileStructA() |  | menuhelp.c | ?? | needs test app
GetPrivateProfileStructW() |  | menuhelp.c | ?? | needs test app
MenuHelp() |  | menuhelp.c | tbtnt | done
ShowHideMenuCtl() |  | menuhelp.c | tbtnt | done
WritePrivateProfileStructA() |  | menuhelp.c | ?? | needs test app
WritePrivateProfileStructW() |  | menuhelp.c | ?? | needs test app
no messages
BUTTON LIST APIs and Messages:
No APIs
BL_ADDBUTTONA |  | btnlist.c | tbtnt | done
BL_ADDBUTTONW |  | btnlist.c | tbtnt | done
BL_DELETEBUTTONA |  | btnlist.c | tbtnt | done
BL_DELETEBUTTONW |  | btnlist.c | tbtnt | done
BL_GETCARETINDEX |  | btnlist.c | tbtnt | done
BL_GETCOUNT |  | btnlist.c | tbtnt | done
BL_GETCURSEL |  | btnlist.c | tbtnt | done
BL_GETITEMDATA |  | btnlist.c | tbtnt | done
BL_GETITEMRECT |  | btnlist.c | tbtnt | done
BL_GETTEXTA |  | btnlist.c | tbtnt | done
BL_GETTEXTLEN |  | btnlist.c | tbtnt | done
BL_GETTEXTW |  | btnlist.c | tbtnt | done
BL_GETTOPINDEX |  | btnlist.c | tbtnt | done
BL_INSERTBUTTONA |  | btnlist.c | tbtnt | done
BL_INSERTBUTTONW |  | btnlist.c | tbtnt | done
BL_RESETCONTENT |  | btnlist.c | tbtnt | done
BL_SETCARETINDEX |  | btnlist.c | tbtnt | done
BL_SETCURSEL |  | btnlist.c | tbtnt | done
BL_SETITEMDATA |  | btnlist.c | tbtnt | done
BL_SETTOPINDEX |  | btnlist.c | tbtnt | done
TRACKBAR APIs and Messages:
No APIs
TBM_CLEARSEL |  | trackbar.c | tbtnt | done
TBM_CLEARTICS |  | trackbar.c | tbtnt | done
TBM_GETCHANNELRECT |  | trackbar.c | ?? | needs testapp
TBM_GETLINESIZE |  | trackbar.c | ?? | needs testapp
TBM_GETNUMTICS |  | trackbar.c | tbtnt | done
TBM_GETPAGESIZE |  | trackbar.c | ?? | needs testapp
TBM_GETPOS |  | trackbar.c | tbtnt | done
TBM_GETPTICS |  | trackbar.c | tbtnt | done
TBM_GETRANGEMAX |  | trackbar.c | tbtnt | done
TBM_GETRANGEMIN |  | trackbar.c | tbtnt | done
TBM_GETSELEND |  | trackbar.c | tbtnt | done
TBM_GETSELSTART |  | trackbar.c | tbtnt | done
TBM_GETTHUMBRECT |  | trackbar.c | ?? | needs testapp
TBM_GETTIC |  | trackbar.c | tbtnt | done
TBM_GETTICPOS |  | trackbar.c | tbtnt | done
TBM_SETLINESIZE |  | trackbar.c | ?? | needs testapp
TBM_SETPAGESIZE |  | trackbar.c | ?? | needs testapp
TBM_SETPOS |  | trackbar.c | tbtnt | done
TBM_SETRANGE |  | trackbar.c | tbtnt | done
TBM_SETRANGEMAX |  | trackbar.c | tbtnt | done
TBM_SETRANGEMIN |  | trackbar.c | tbtnt | done
TBM_SETSEL |  | trackbar.c | tbtnt | done
TBM_SETSELEND |  | trackbar.c | tbtnt | done
TBM_SETSELSTART |  | trackbar.c | tbtnt | done
TBM_SETTIC |  | trackbar.c | tbtnt | done
TBM_SETTICFREQ |  | trackbar.c | ?? | needs testapp
DRAGLIST APIs and Messages:
DrawInsert() |  | draglist.c | ??? | needs testapp
LBItemFromPt() |  | draglist.c | ??? | needs testapp
MakeDragList() |  | draglist.c | ??? | needs testapp
DL_BEGINDRAG |  | tbcust.c | ??? | needs testapp
DL_CANCELDRAG |  | tbcust.c | ??? | needs testapp
DL_DRAGGING |  | tbcust.c | ??? | needs testapp
DL_DROPPED |  | tbcust.c | ??? | needs testapp
UP-DOWN / SPINNER APIs and Messages:
CreateUpDownControl() |  | updown.c | tbtnt | done
UDM_GETACCEL |  | updown.c | tbtnt | done
UDM_GETBASE |  | updown.c | tbtnt | done
UDM_GETBUDDY |  | updown.c | tbtnt | done
UDM_GETPOS |  | updown.c | tbtnt | done
UDM_GETRANGE |  | updown.c | tbtnt | done
UDM_SETACCEL |  | updown.c | tbtnt | done
UDM_SETBASE |  | updown.c | tbtnt | done
UDM_SETBUDDY |  | updown.c | tbtnt | done
UDM_SETPOS |  | updown.c | tbtnt | done
UDM_SETRANGE |  | updown.c | tbtnt | done
PROGRESS BAR APIs and Messages:
No APIs
PBM_DELTAPOS |  | progress.c | tbtnt | done
PBM_SETPOS |  | progress.c | tbtnt | done
PBM_SETRANGE |  | progress.c | tbtnt | done
PBM_SETSTEP |  | progress.c | tbtnt | done
PBM_STEPIT |  | progress.c | tbtnt | done
HOTKEY APIs and Message:
No APIs
HKM_GETHOTKEY |  | (hotkey.c) | ?? | needs dll and testapp
HKM_SETHOTKEY |  | (hotkey.c) | ?? | needs dll and testapp
HKM_SETRULES |  | (hotkey.c) | ?? | needs dll and testapp
TAB CONTROLS APIs and Messages:
TabCtrl_AdjustRect() |  | commctrl.h | tabtest | done
TabCtrl_DeleteAllItems() |  | commctrl.h | tabtest | done
TabCtrl_DeleteItem() |  | commctrl.h | tabtest | done
TabCtrl_GetBkColor() |  | commctrl.h | tabtest | done
TabCtrl_GetCurSel() |  | commctrl.h | tabtest | done
TabCtrl_GetImageList() |  | commctrl.h | tabtest | done
TabCtrl_GetItemA() |  | commctrl.h | tabtest | done
TabCtrl_GetItemCount() |  | commctrl.h | tabtest | done
TabCtrl_GetItemRect() |  | commctrl.h | tabtest | done
TabCtrl_GetItemW() |  | commctrl.h | tabtest | done
TabCtrl_GetRowCount() |  | commctrl.h | ?? | needs testapp
TabCtrl_GetTextBkColor() |  | commctrl.h | tabtest | done
TabCtrl_GetTextColor() |  | commctrl.h | tabtest | done
TabCtrl_GetToolTips() |  | commctrl.h | ?? | needs testapp
TabCtrl_HitTest() |  | commctrl.h | tabtest | done
TabCtrl_InsertItemA() |  | commctrl.h | tabtest | done
TabCtrl_InsertItemW() |  | commctrl.h | tabtest | done
TabCtrl_RemoveImage() |  | commctrl.h | ?? | needs testapp
TabCtrl_SetBkColor() |  | commctrl.h | tabtest | done
TabCtrl_SetCurSel() |  | commctrl.h | tabtest | done
TabCtrl_SetImageList() |  | commctrl.h | tabtest | done
TabCtrl_SetItemA() |  |  | tabtest
TabCtrl_SetItemExtra() |  | commctrl.h | ?? | needs testapp
TabCtrl_SetItemSize() |  | commctrl.h | ?? | needs testapp
TabCtrl_SetItemW() |  | commctrl.h | tabtest | Not Unicoded yet
TabCtrl_SetPadding() |  | commctrl.h | ?? | needs testapp
TabCtrl_SetTextBkColor() |  | commctrl.h | ?? | needs testapp
TabCtrl_SetTextColor() |  | commctrl.h | ?? | needs testapp
TabCtrl_SetToolTips() |  | commctrl.h | ?? | needs testapp
TCM_ADJUSTRECT |  | tab.c |  | needs testapp
TCM_DELETEALLITEMS |  | tab.c |  | needs testapp
TCM_DELETEITEM |  | tab.c |  | needs testapp
TCM_GETBKCOLOR |  | ?? | ?? | needs dll and testapp
TCM_GETCURSEL |  | tab.c |  | needs testapp
TCM_GETIMAGELIST |  | tab.c |  | needs testapp
TCM_GETITEM |  | tab.c |  | needs testapp
TCM_GETITEMCOUNT |  | tab.c |  | needs testapp
TCM_GETITEMRECT |  | tab.c |  | needs testapp
TCM_GETROWCOUNT |  | tab.c |  | needs testapp
TCM_GETTEXTBKCOLOR |  | ?? |  | needs dll and testapp
TCM_GETTEXTCOLOR |  | ?? |  | needs dll and testapp
TCM_GETTOOLTIPS |  | ?? |  | needs dll and testapp
TCM_HITTEST |  | tab.c |  | needs testapp
TCM_INSERTITEMA |  | tab.c |  | needs testapp
TCM_INSERTITEMW |  | tab.c |  | needs testapp
TCM_REMOVEIMAGE |  | tab.c |  | needs testapp
TCM_SETBKCOLOR |  | ?? | ?? | needs dll and testapp
TCM_SETCURSEL |  | tab.c |  | needs testapp
TCM_SETIMAGELIST |  | tab.c |  | needs testapp
TCM_SETITEM |  | tab.c |  | needs testapp
TCM_SETITEMEXTRA |  | tab.c |  | needs testapp
TCM_SETITEMSIZE |  | tab.c |  | needs testapp
TCM_SETPADDING |  | tab.c |  | needs testapp
TCM_SETTEXTBKCOLOR |  | ?? |  | needs dll and testapp
TCM_SETTEXTCOLOR |  | ?? |  | needs dll and testapp
TCM_SETTOOLTIPS |  | ?? |  | needs dll and testapp
HEADER BAR APIs and Messages
Header_DeleteItem() |  | commctrl.h | headtest | done
Header_GetItemA() |  |  | headtest
Header_GetItemCount() |  | commctrl.h | headtest | done
Header_GetItemW() |  | commctrl.h | headtest | Not Unicoded yet
Header_InsertItemA() |  |  | headtest
Header_InsertItemW() |  | commctrl.h | headtest | Not Unicoded yet
Header_Layout() |  | commctrl.h | headtest | done
Header_SetItemA() |  |  | headtest
Header_SetItemW() |  | commctrl.h | headtest | Not Unicoded yet
HDM_DELETEITEM |  | header2.c |  | Needs testapp
HDM_GETITEMA |  |  |  | Needs testapp
HDM_GETITEMCOUNT |  | header2.c |  | Needs testapp
HDM_GETITEMW |  | header2.c |  | Needs testapp
HDM_INSERTITEMA |  |  |  | Needs testapp
HDM_INSERTITEMW |  | header2.c |  | Needs testapp
HDM_LAYOUT |  | header2.c |  | Needs testapp
HDM_SETITEMA |  |  |  | Needs testapp
HDM_SETITEMW |  | header2.c |  | Needs testapp
HDN_BEGINTRACK |  | (lvrept.c) |  | ??
HDN_DIVIDERCLICK |  | (lvrept.c) |  | ??
HDN_DIVIDERDBLCLICK |  | (lvrept.c) |  | ??
HDN_ENDTRACK |  | (lvrept.c) |  | ??
HDN_ITEMCHANGED |  | (lvrept.c) |  | ??
HDN_ITEMCHANGING |  | (lvrept.c) |  | ??
HDN_ITEMCLICK |  | (lvrept.c) |  | ??
HDN_ITEMDBLCLICK |  | (lvrept.c) |  | ??
HDN_TRACK |  | (lvrept.c) |  | ??
TOOLTIPS APIs and Messages:
No APIs
TTM_ACTIVATE |  | tooltips.c | ?? | Needs testapp
TTM_ADDTOOL |  | tooltips.c | ?? | Needs testapp
TTM_DEACTIVATE |  | tooltips.c | ?? | Needs testapp
TTM_DELTOOL |  | tooltips.c | ?? | Needs testapp
TTM_GETTEXT |  | tooltips.c | ?? | Needs testapp
TTM_GETTOOLINFOA |  |  | ??
TTM_GETTOOLINFOW |  | tooltips.c | ?? | Needs testapp
TTM_HITTEST |  | tooltips.c | ?? | Needs testapp
TTM_NEWTOOLRECT |  | tooltips.c | ?? | Needs testapp
TTM_RELAYEVENT |  | tooltips.c | ?? | Needs testapp
TTM_SETDELAYTIME |  | tooltips.c | ?? | Needs testapp
TTM_SETTOOLINFOA |  |  | ??
TTM_SETTOOLINFOW |  | tooltips.c | ?? | Needs testapp
TTM_UPDATETIPTEXT |  | tooltips.c | ?? | Needs testapp
TTN_NEEDTEXT |  | tab.c | ?? | Needs testapp
IMAGELIST APIs and Messages:
In Progress
ImageList_Add() |  | image.c | imglst
ImageList_AddFromImageList() |  | image.c | imglst
ImageList_AddIcon() |  | image.c | imglst
ImageList_AddMasked() |  | image.c | imglst
ImageList_CopyDitherImage() |  | image.c | imglst
ImageList_Create() |  | image.c | imglst
ImageList_Destroy() |  | image.c | imglst
ImageList_DragMove() |  | image.c | imglst
ImageList_DragShow() |  | image.c | imglst
ImageList_Draw() |  | image.c | imglst
ImageList_Draw2() |  | image.c | ?? | Needs testapp
ImageList_EndDrag() |  | image.c | imglst
ImageList_ExtractIcon() |  | image.c | imglst
ImageList_GetBkColor() |  | image.c | imglst
ImageList_GetIconSize() |  | image.c | imglst
ImageList_GetImageCount() |  | image.c | imglst
ImageList_GetImageInfo() |  | image.c | imglst
ImageList_GetImageRect() |  | image.c | imglst
ImageList_LoadBitmapA() |  |  | imglst
ImageList_LoadBitmapW() |  | image.c | imglst | Not Unicoded yet
ImageList_Merge() |  | image.c | imglst
ImageList_Remove() |  | image.c | imglst
ImageList_Replace() |  | image.c | imglst
ImageList_ReplaceIcon() |  | image.c | imglst
ImageList_SetBkColor() |  | image.c | imglst
ImageList_SetObjectOwner() |  | image.c | ?? | Needs testapp
ImageList_SetOverlayImage() |  | image.c | ?? | Needs testapp
ImageList_StartDrag() |  | image.c | imglst
No Messages
LISTVIEW APIs and Messages:
Waiting for ImageList
ListView_Arrange() |  | commctrl.h | listtest
ListView_CreateDragImage() |  | commctrl.h | ?? | Needs testapp
ListView_DeleteAllItems() |  | commctrl.h | listtest
ListView_DeleteColumn() |  | commctrl.h | listtest
ListView_DeleteItem() |  | commctrl.h | listtest
ListView_EditLabel() |  | commctrl.h | listtest
ListView_EnsureVisible() |  | commctrl.h | listtest
ListView_FindItemA() |  |  | listtest
ListView_FindItemW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_GetBkColor() |  | commctrl.h | listtest
ListView_GetCallbackMask() |  | commctrl.h | listtest
ListView_GetColumnA() |  |  | listtest
ListView_GetColumnW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_GetColumnWidth() |  | commctrl.h | listtest
ListView_GetCountPerPage() |  | commctrl.h | ?? | Needs testapp
ListView_GetEditControl() |  | commctrl.h | listtest
ListView_GetImageList() |  | commctrl.h | listtest
ListView_GetItemA() |  |  | listtest
ListView_GetItemCount() |  | commctrl.h | listtest
ListView_GetItemPosition() |  | commctrl.h | listtest
ListView_GetItemRect() |  | commctrl.h | listtest
ListView_GetItemState() |  | commctrl.h | listtest
ListView_GetItemTextA() |  |  | listtest
ListView_GetItemTextW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_GetItemW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_GetNextItem() |  | commctrl.h | listtest
ListView_GetOrigin() |  | commctrl.h | listtest
ListView_GetStringWidthA() |  |  | listtest
ListView_GetStringWidthW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_GetTextBkColor() |  | commctrl.h | listtest
ListView_GetTextColor() |  | commctrl.h | listtest
ListView_GetTopIndex() |  | commctrl.h | ?? | Needs testapp
ListView_GetViewRect() |  | commctrl.h | listtest
ListView_HitTest() |  | commctrl.h | listtest
ListView_InsertColumnA() |  |  | listtest
ListView_InsertColumnW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_InsertItemA() |  |  | listtest
ListView_InsertItemW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_RedrawItems() |  | commctrl.h | listtest
ListView_Scroll() |  | commctrl.h | listtest
ListView_SetBkColor() |  | commctrl.h | listtest
ListView_SetCallbackMask() |  | commctrl.h | listtest
ListView_SetColumnA() |  |  | listtest
ListView_SetColumnW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_SetColumnWidth() |  | commctrl.h | listtest
ListView_SetImageList() |  | commctrl.h | listtest
ListView_SetItemA() |  |  | listtest
ListView_SetItemCount() |  | commctrl.h | ?? | Needs testapp
ListView_SetItemPosition() |  | commctrl.h | listtest
ListView_SetItemStateA() |  |  | listtest
ListView_SetItemStateW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_SetItemTextA() |  |  | listtest
ListView_SetItemTextW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_SetItemW() |  | commctrl.h | listtest | Not Unicoded yet
ListView_SetTextBkColor() |  | commctrl.h | listtest
ListView_SetTextColor() |  | commctrl.h | listtest
ListView_SortItems() |  | commctrl.h | ?? | Needs testapp
ListView_Update() |  | commctrl.h | ?? | Needs testapp
LVM_ARRANGE |  | listview.c | listtest
LVM_CREATEDRAGIMAGE |  | listview.c | listtest
LVM_DELETEALLITEMS |  | listview.c | listtest
LVM_DELETECOLUMN |  | listview.c | listtest
LVM_DELETEITEM |  | listview.c | listtest
LVM_EDITLABEL |  | listview.c | listtest
LVM_ENSUREVISIBLE |  | listview.c | listtest
LVM_FINDITEMA |  |  | listtest
LVM_FINDITEMW |  | listview.c | listtest
LVM_GETBKCOLOR |  | listview.c | listtest
LVM_GETCALLBACKMASK |  | listview.c | listtest
LVM_GETCOLUMNA |  |  | listtest
LVM_GETCOLUMNW |  | listview.c | listtest
LVM_GETCOLUMNWIDTH |  | listview.c | listtest
LVM_GETCOUNTPERPAGE |  | listview.c | listtest
LVM_GETEDITCONTROL |  | listview.c | listtest
LVM_GETIMAGELIST |  | listview.c | listtest
LVM_GETITEMA |  |  | listtest
LVM_GETITEMCOUNT |  | listview.c | listtest
LVM_GETITEMPOSITION |  | listview.c | listtest
LVM_GETITEMRECT |  | listview.c | listtest
LVM_GETITEMSTATE |  | listview.c | listtest
LVM_GETITEMTEXTA |  |  | listtest
LVM_GETITEMTEXTW |  | listview.c | listtest
LVM_GETITEMW |  | listview.c | listtest
LVM_GETNEXTITEM |  | listview.c | listtest
LVM_GETOPINDEX |  | listview.c | listtest
LVM_GETORIGIN |  | listview.c | listtest
LVM_GETSTRINGWIDTHA |  |  | listtest
LVM_GETSTRINGWIDTHW |  | listview.c | listtest
LVM_GETTEXTBKCOLOR |  | listview.c | listtest
LVM_GETTEXTCOLOR |  | listview.c | listtest
LVM_GETVIEWRECT |  | listview.c | listtest
LVM_HITTEST |  | listview.c | listtest
LVM_INSERTCOLUMNA |  |  | listtest
LVM_INSERTCOLUMNW |  | listview.c | listtest
LVM_INSERTITEMA |  |  | listtest
LVM_INSERTITEMW |  | listview.c | listtest
LVM_REDRAWITEMS |  | listview.c | listtest
LVM_SCROLL |  | listview.c | listtest
LVM_SETBKCOLOR |  | listview.c | listtest
LVM_SETCALLBACKMASK |  | listview.c | listtest
LVM_SETCOLUMNA |  |  | listtest
LVM_SETCOLUMNW |  | listview.c | listtest
LVM_SETCOLUMNWIDTH |  | listview.c | listtest
LVM_SETIMAGELIST |  | listview.c | listtest
LVM_SETITEMA |  |  | listtest
LVM_SETITEMCOUNT |  | listview.c | listtest
LVM_SETITEMPOSITION |  | listview.c | listtest
LVM_SETITEMSTATEA |  |  | listtest
LVM_SETITEMSTATEW |  | listview.c | listtest
LVM_SETITEMTEXTA |  |  | listtest
LVM_SETITEMTEXTW |  | listview.c | listtest
LVM_SETITEMW |  | listview.c | listtest
LVM_SETTEXTBKCOLOR |  | listview.c | listtest
LVM_SETTEXTCOLOR |  | listview.c | listtest
LVM_SORTITEMS |  | listview.c | listtest
LVM_UPDATE |  | listview.c | listtest
LVN_BEGINDRAG |  | ???
LVN_BEGINLABELEDIT |  | ???
LVN_BEGINRDRAG |  | ???
LVN_COLUMNCLICK |  | ???
LVN_DELETEALLITEMS |  | ???
LVN_DELETEITEM |  | ???
LVN_ENDDRAG |  | ???
LVN_ENDLABELEDIT |  | ???
LVN_ENDRDRAG |  | ???
LVN_GETDISPINFO |  | ???
LVN_INSERTITEM |  | ???
LVN_ITEMCHANGED |  | ???
LVN_ITEMCHANGING |  | ???
LVN_KEYDOWN |  | ???
LVN_PEN |  | ???
LVN_SETDISPINFO |  | ???
TREEVIEW APIs and Messages:
Waiting for ImageList
TreeView_CreateDragImage() |  | commctrl.h | ??
TreeView_DeleteAllItems() |  | commctrl.h | ??
TreeView_DeleteItem() |  | commctrl.h | ??
TreeView_EditLabel() |  | commctrl.h | ??
TreeView_EnsureVisible() |  | commctrl.h | ??
TreeView_Expand() |  | commctrl.h | ??
TreeView_GetChild() |  | commctrl.h | ??
TreeView_GetCount() |  | commctrl.h | ??
TreeView_GetDropHilight() |  | commctrl.h | ??
TreeView_GetEditControl() |  | commctrl.h | ??
TreeView_GetFirstVisible() |  | commctrl.h | ??
TreeView_GetImageList() |  | commctrl.h | ??
TreeView_GetIndent() |  | commctrl.h | ??
TreeView_GetItemA() |  |  | ??
TreeView_GetItemRect() |  | commctrl.h | ??
TreeView_GetItemW() |  | commctrl.h | ?? | Not Unicoded yet
TreeView_GetNextItem() |  | commctrl.h | ??
TreeView_GetNextSibling() |  | commctrl.h | ??
TreeView_GetNextVisible() |  | commctrl.h | ??
TreeView_GetParent() |  | commctrl.h | ??
TreeView_GetPrevSibling() |  | commctrl.h | ??
TreeView_GetPrevVisible() |  | commctrl.h | ??
TreeView_GetRoot() |  | commctrl.h | ??
TreeView_GetSelection() |  | commctrl.h | ??
TreeView_GetVisibleCount() |  | commctrl.h | ??
TreeView_HitTest() |  | commctrl.h | ??
TreeView_InsertItemA() |  |  | ??
TreeView_InsertItemW() |  | commctrl.h | ?? | Not Unicoded yet
TreeView_Select() |  | commctrl.h | ??
TreeView_SelectDropTarget() |  | commctrl.h | ??
TreeView_SelectItem() |  | commctrl.h | ??
TreeView_SetImageList() |  | commctrl.h | ??
TreeView_SetIndent() |  | commctrl.h | ??
TreeView_SetItemA() |  |  | ??
TreeView_SetItemW() |  | commctrl.h | ?? | Not Unicoded yet
TreeView_SortChildren() |  | commctrl.h | ??
TreeView_SortChildrenCB() |  | commctrl.h | ??
TVM_CREATEDRAGIMAGE |  | treeview.c | ??
TVM_DELETEITEM |  | treeview.c | ??
TVM_EDITLABEL |  | treeview.c | ??
TVM_ENSUREVISIBLE |  | treeview.c | ??
TVM_EXPAND |  | treeview.c | ??
TVM_GETCOUNT |  | treeview.c | ??
TVM_GETICONCONTROL |  | treeview.c | ??
TVM_GETIMAGELIST |  | treeview.c | ??
TVM_GETINDENT |  | treeview.c | ??
TVM_GETITEMA |  |  | ??
TVM_GETITEMRECT |  | treeview.c | ??
TVM_GETITEMW |  | treeview.c | ??
TVM_GETNEXTITEM |  | treeview.c | ??
TVM_GETVISIBLECOUNT |  | treeview.c | ??
TVM_HITTEST |  | treeview.c | ??
TVM_INSERTITEMA |  |  | ??
TVM_INSERTITEMW |  | treeview.c | ??
TVM_SELECTITEM |  | treeview.c | ??
TVM_SETIMAGELIST |  | treeview.c | ??
TVM_SETINDENT |  | treeview.c | ??
TVM_SETITEMA |  |  | ??
TVM_SETITEMW |  | treeview.c | ??
TVM_SORTCHILDREN |  | treeview.c | ??
TVM_SORTCHILDRENCB |  | treeview.c | ??
TVN_BEGINDRAG |  | ??? | ??
TVN_BEGINLABELEDIT |  | ??? | ??
TVN_BEGINRDRAG |  | ??? | ??
TVN_DELETEITEM |  | ??? | ??
TVN_ENDLABELEDIT |  | ??? | ??
TVN_GETDISPINFO |  | ??? | ??
TVN_ITEMEXPANDED |  | ??? | ??
TVN_ITEMEXPANDING |  | ??? | ??
TVN_KEYDOWN |  | ??? | ??
TVN_SELCHANGED |  | ??? | ??
TVN_SELCHANGING |  | ??? | ??
TVN_SETDISPINFO |  | ??? | ??